## Sheet1
Team Number: | 19 |  | PROJECT: |  | TeamChat |  | at: | 2022-10-18
|  |  | Team Member's Name & Role: | 1 | Luka Nikolaisvili
|  |  |  | 2 | Drew Hubble
|  |  |  | 3 | Yanxin Wang
|  |  |  | 4 | Chukwudubem Ilo
|  |  |  | 5 | Taiwo Bolanle
[7 empty] | LEVEL OF | ESTIMATED
|  | WEEKS | DAYS |  |  | ASSIGNED | COMPLEXITY | EFFORT
WEEK OF | SPRINT | LEFT | ELAPSED |  | PRODUCT DELIVERABLES / FEATURES TO BE COMPLETED | TO | [0-3] | HOURS
2022-09-15 | 0 | 10 | 0 | 1 | Preliminary Project Ideas | Team | 1 | 3
|  |  |  | 2 | Team SWOT Form | Team | 1 | 1
|  |  |  | 3 | Project Approval Request Form | Drew | 1 | 1
|  |  |  | 4 | Team Organization Chart | Drew | 3 | 3
2022-09-22 | 0 | 9 | 7 | 5 | Product Features Priority Template | Team | 2 | 2
2022-09-29 | 1 | 8 | 14 | 1 | Project Charter | Luka | 2 | 2
|  |  |  | 2 | Create Kanboard tickets | Drew | 0 | 0.5
|  |  |  | 2 | Project Deliverables Schedule | Drew | 2 | 3
2022-10-06 | 1 | 7 | 21 | 2 | Project WBS Chart | Drew | 1 | 2
|  |  |  | 3 | Setting up the git repositories for collaborational work | Yanxin | 1 | 1
|  |  |  | 4 | User stories for website | Emman | 2 | 1
|  |  |  | 5 | Lessons Learned Report #1 | Taiwo | 0 | 1
2022-10-13 | 2 | 6 | 28 | 1 | APIs used: list all API’s used, for what and how | Luka | 2 | 2
|  |  |  | 2 | Create Kanboard tickets | Drew | 0 | 0.5
|  |  |  | 4 | User flow diagram for the website | Emman | 2 | 2
|  |  |  | 5 | Class diagram for backend functionality | Taiwo | 2 | 2
2022-10-20 | 2 | 5 | 35 | 1 | Test cases for backend | Luka | 2 | 2
|  |  |  | 2 | Database diagram | Drew | 2 | 2
|  |  |  | 3 | Website code - basic framework | Yanxin | 2 | 5
2022-10-27 | 3 | 4 | 42 | 1 | Lessons Learned Report #2 | Luka | 1 | 1
|  |  |  | 2 | Create Kanboard tickets | Drew | 0 | 0.5
RB |  |  |  | 3 | Website code - website connection to back end functionality | Yanxin | 3 | 4
|  |  |  | 4 | Website code - Web pages with button functionality | Emman | 2 | 4
|  |  |  | 5 | Back-end code - API messaging Implementation | Taiwo | 3 | 5
2022-11-03 | 3 | 3 | 49 | 1 | Back-end testing - API messaging testing | Luka | 2 | 3
|  |  |  | 2 | Website Code - User Login/Sign-up | Drew | 2 | 3
|  |  |  | 2 | Database code | Drew | 2 | 4
|  |  |  | 3 | Website Code - User Profile Page | Yanxin | 2 | 3
|  |  |  | 5 | Lessons Learned Report #3 | Taiwo | 1 | 1
2022-11-10 | 4 | 2 | 56 | 1 | Back-end code - home page feed implementation | Luka | 3 | 5
|  |  |  | 2 | Create Kanboard tickets | Drew | 0 | 0.5
|  |  |  | 2 | Database - testing document | Drew | 2 | 1
2022-11-17 | 4 | 1 | 63 | 2 | Finished presentation - PowerPoint slides | Drew | 1 | 3
|  |  |  | 3 | Testing document - website functionality (working as intended) | Yanxin | 2 | 2
|  |  |  | 4 | Website code - All web pages with a common format | Emman | 2 | 5
|  |  |  | 5 | Back-end testing - home page feed testing | Taiwo | 2 | 3
2022-11-23 |  | 0 | 69 |  | PROJECT DUE BY MIDNIGHT ON WEDNESDAY, NOVEMBER 23
[7 empty] | TOTAL ESTIMATED EFFORT HOURS: | 84
[ see next page for unscheduled product backlog ]
[7 empty] | LEVEL | INITIAL
[7 empty] | OF | ESTIMATED
[7 empty] | COMPLEXITY | EFFORT
[5 empty] | UNSCHEDULED PRODUCT BACKLOG DELIVERABLES / FEATURES |  | [0-3] | HOURS
[5 empty] | Infinity Scroll - Back-end Code |  | 2 | 2
[5 empty] | Group Forum Code - Back-end Code |  | 3 | 4
[5 empty] | Like/share/coomment functionality - Back-end Code |  | 3 | 3
[5 empty] | Private/Public Account functionality - Back-end Code |  | 2 | 2
TOTAL ESTIMATED UNSCHEDULED EFFORT HOURS: